Affordable Learning Georgia Affordable Materials Grants
Continuous Improvement Grants Final Report

(or Mini-Grants, for R17 and earlier)

# General Information

Date: 1 July 2021

Grant Round: 17

Grant Number: M123

Institution Name(s): Savannah State University

Team Members (Name, Title, Department, Institutions if different, and email address for each):

Jenni G Halpin, Associate Professor of English, Department of English, Languages, and Cultures

Jonathan Elmore, Associate Professor of English, Department of English, Languages, and Cultures

Project Lead: Halpin

Course Name(s) and Course Numbers: ENGL 2121 (British Literature I)

Final Semester of Project: Summer 2021

If applicable to your project:

Average Number of Students Per Course Section: 30 (at SSU)

Number of Course Sections Affected by Implementation of Revised Resources: 1-2 per year (at SSU)

Total Number of Students Affected by Implementation of Revised Resources: 20-60 per year (at SSU)

# Project Narrative

Describe the course of your revision or ancillary creation project, including

- A summary of your project’s purpose, plan, and timeline.

- The original works which were revised or added to, with links. For example, if you revised an open textbook, give the title, author, and link.

- A narrative description of how the project’s plan was carried out.

- Lessons learned, including anything you would do differently next time.

Our project’s purpose was the creation of an ancillary OER to facilitate the centering of African and Afro-Diasporic peoples in the early survey of British literature (ENGL 2121).

In summer 2020 we developed a draft table of contents, identifying materials extant and materials in need of development, and we developed a set of interview questions for our interview subjects. Throughout the academic year 2020-2021 we continued to produce content and sent and received interview responses. In summer 2021 we finished drafting materials, confirmed revised text of interviews with the interviewees, and edited the full text into an accessible PDF document.

We believe our process worked well. Elements of our workflow that were particularly helpful included: regular meetings between the team members (monthly in semester, every other week in summer), consistent identification of next steps and benchmarks to be achieved prior to the next meeting, attention to final production details during the drafting process (e.g. consideration of citation styles and accessibility needs) such that the final production required minimal editing and formatting, and wide reading and research continued throughout the process.

# Materials Description

Describe all the materials you have created or revised as part of this project. These descriptions may be used in the OpenALG repository description field.

An Introduction to African and Afro-Diasporic Peoples and Influences in British Literature and Culture before the Industrial Revolution is a supplemental textbook designed to introduce students to the lives, influences, and contributions of Africans and their descendants in Britain prior to the Industrial Revolution and reaching back to the Roman occupation of the British Isles. This text is appropriate for introductory undergraduate survey courses as well as upper level undergraduate courses in literary and cultural studies.

# Materials Links

If you are hosting your materials in places other than OpenALG, please provide these links in this section. Otherwise, leave blank. Note: we cannot access D2L or Canvas links.

# Future Plans

- Describe any planned or actual papers, presentations, publications, or other professional activities that you expect to produce that reflect your work on this project.

- Describe any plans to revise or add to these materials in the future.

The most obvious next step is to produce a similar resource for British Literature II. As both of us continue to share the teaching of ENGL 2121 and ENGL 2122 almost exclusively between us at SSU, we are well positioned to recognize when this OER will come into need for updating or extension. We are considering developing plans for a single OER textbook which would replace both the supplement produced under the current minigrant and a typical literature anthology, but at this time the granting standards of ALG, particularly that the impact weighting considers only the number of students on the grantee’s campus rather than the number of students potentially impacted in the system, do not make us confident that applying would be a good use of our time.