## Slide 1: Unit 11: Leading and Facilitating Change
Slides compiled by Dr. Shahriar

## Slide 2
Tell me and I’ll forget;
show me and I may remember;
involve me and I’ll understand.
– Chinese Proverb
Notes: Leading and facilitating change is about working with people. If I were to sum up this unit in one sentence, it would be this Chinese proverb:
  Tell me and I’ll forget;
  show me and I may remember;
  involve me and I’ll understand.
To me, involvement is a key concept in change management. Involving people to the extent possible does three things 1) it builds understanding, a shared pool of knowledge, 2) it offers an invitation to engage in the project and influence outcomes, and 3) it provides additional eyes, ears, knowledge, experience and perspectives to inform the work.

## Slide 3: Objectives
Explain concerns expressed by participants in a process analysis & redesign scenario in terms of common change management concepts.
Propose strategies to gain acceptance of changes in work processes.
Create and critique a facilitation plan, including appropriate facilitation tools for a given process analysis & redesign scenario.
Given a health care change management scenario, explain outcomes in terms of common change management concepts.
Notes: After this unit, you should be able to:
Explain concerns expressed by participants in a process analysis & redesign scenario in terms of common change management concepts.
Propose strategies to gain acceptance of changes in work processes.
Create and critique a facilitation plan, including appropriate facilitation tools for a given process analysis & redesign scenario, and
Given a health care change management scenario, explain outcomes in terms of common change management concepts.

## Slide 4: Topics
Change Management concepts
Tools for facilitating change
Facilitation planning
Notes: The topics covered in Unit 9 include:
  Change management concepts,
  Tools for facilitating change, and
  Facilitation planning.

## Slide 5: Change Concepts
What is it that causes some change management efforts to be successful?
Notes: There has been a lot of work in change management, hundreds of books on the topic, and many different perspectives. It is impossible to cover everything in one unit. Thus, we will cover main points and provide some tools that practitioners can use.
To start off, we will cover some key concepts of change and change management, more things like staff involvement. These key change concepts can be called upon by practitioners for use in future change efforts. These key concepts help explain what is it that causes the successful change management efforts to be successful, and others to fail.

## Slide 6: Employee’s perspective
Regulatory
Changes
Market
Changes
Departmental
Changes
Personnel
changes
Requests
From
Manager
Re-
structuring
Work
Process
Change
Merger /
Acquisition
Project
change
Employee
From the employee’s perspective, there can be a lot of changes, and a lot of changes can be overwhelming.
Remember that work process change may be only one of several changes an organization is undergoing.
Notes: From the employee’s perspective, there can be a lot of changes and a lot of changes can be overwhelming. Remember that work process change may be only one of several changes an organization is undergoing. Employees are often dealing simultaneously with regulatory and market changes that result in new job requirements, organizational changes, and process improvements all at once; expect no different in clinics today.

## Slide 7: Janssen’s 4-Room Apartment1
Reproduced from http://www.claesjanssen.com/four-rooms/about-the-four-rooms-of-change/index.shtml
Contentment
Denial
Confusion
Renewal
A personally
significant
change occurs
Notes: Claes F Janssen conceptualized the Four Rooms Theory of Change, also called the 4-Room Apartment1. He discusses changes that are usually very negatively significant to a person. (Death or ending of an important relationship is the usual example, but this could also be something that has the perceived potential to change one’s life, including job changes, fear of loss of power, loss of importance, etc.).
When one of these significant changes occurs, the individual moves from the current content state into denial, then into a state of confusion, possible uncertainty about the future or about how the individual can deal with the situation. Out of confusion, once the individual has worked through the confusion, comes growth and renewal, then once again, contentment comes.
Simply put, at the end of every storm, fair weather returns. It is important for people working in change management situations to understand that this is an individual process, likely dependent on how the individual perceives the change, i.e., how threatened (rational or not) the individual is. Also, each individual moves through the state at his/her own pace. Thus, when you approach a room of people, you will likely not know who perceives a possible threat or loss, and where in the process that person is.

## Slide 8: Key Concept 1:
Humans and organizations are complex
Many factors that come into play
  Organizational constraints
  Management style
  Organizational, departmental, division, and personal goals
  Personalities
  Environmental factors
Notes: Many puzzle over the success and failure of Change Management efforts. One reason is that change management involves humans and organizations, i.e., complex situations with many different factors.
Some of these include:
  Organizational constraints (lack of money or people with needed skills, or just enough people),
  Management style (dictatorship versus democracy),
  Organizational goals and departmental, division, and personal goals not necessarily in alignment,
  Personalities,
  Environmental factors (for example, new regulations that force change),
  Etc.
In multi-factor situations, attribution of cause and effect is often challenging.

## Slide 9: Key Concept 2:
Organizations are living, changing biological systems
  If you push on the system, it will compensate
  Behavior dependent on culture and level of trust
Reductionist treatment rarely explains the whole
  Measures and numbers
    Are not complete
    Cannot capture the complete complexity.
Notes: Organizations (governments, societies, processes, that are comprised of people) are living, changing biological systems. If you try to change the system, it will compensate. The behavior of the system and individuals in it is likely dependent on the organizational culture and level of trust in leadership and trust in colleagues.
Mechanistic tools like quantitative measurement, science and engineering are valuable in providing information for better decision making and managing and must be used in the context of an understanding of the natural system. However, such reductionist treatment rarely explains the whole.

## Slide 10: Key Concept 3:
Change happens through individual choice and freedom not through top-down control or coercion.
it is imperative that every person’s right to choose at some level be respected, not to say that everything is the employee’s choice
Notes: Change happens through individual choice and freedom, not through top-down control or coercion. This is not a statement that all organizations should be democracies. As we saw in unit 7, there are many different leadership styles ranging from one person making all the decisions to group decisions. What Key Concept 3 is saying is that it is imperative that every person’s right to choose at some level be respected. The choice may be whether or not to be part of the effort, whether or not to provide input, or in an extreme case, whether or not to continue working at an organization. Key Concept 3 does not say that everything is the employee’s choice, this is usually not feasible. But, change leaders should be clear about what choices employees have and should respect those choices.

## Slide 11: Key Concept 4:
John Gall, MD in his 1970’s book Systemantics2 said it most insightfully: Systems run best when designed to run downhill.
People will do things if they are easy. Processes that require extra steps are less likely to be followed
For example, asking staff to manually write down or note each hypertension patient for a quality improvement project is hard; versus pulling the list from the data that are captured during the visit, which is easy
Notes: John Gall, MD in his 1970’s book Systemantics 2 said it most insightfully: Systems run best when designed to run downhill. This is really the intersection between process analysis and redesign and change management. People will do things if they are easy. Processes that require extra steps are less likely to be followed.
For example, asking staff to manually write down or note each hypertension patient for a quality improvement project is hard; versus pulling the list from the data that are captured during the visit, which is easy. If it adds extra steps, it is a problem.

## Slide 12: Key Concept 4 Example:
Sure, walk in my garden !
Notes: I have a great example of systems running (or not) downhill. I lived in a loft in an old warehouse. There was a garden area encased in old railroad ties between the parking lot and the door. There was one place where everyone cut through the garden and it created an ugly area where nothing grew. Some insightful person bought some stepping stones and put them in the path. The garden was no longer an obstacle between the car and the door. It became a beautiful addition to our building and people automatically used the path. The person who added the stones was very insightful. Where others would have put up signs or fences, the stone putter found a way for the people and the garden to happily co-exist.
Another great example of this principle is in the movie Out of Africa, the 1985 movie starring Meryl Streep and Robert Redford, set in early 1900s Kenya. The Baroness, played by Meryl Streep, is trying to start a coffee plantation in Kenya in the early 1900’s. She directs the natives to re-route a river. They plead with her, explaining that it won’t work, that “the river will have her way” in the end, but she does not listen. Toward the end of the movie, a storm comes and washes the dam out. Process design and change management is similar in that the designer has to work with and listen to people in the facility, and combine their information with best practice to find “the downhill way.”

## Slide 13: Key Concept 5:
Change starts with a deeply meaningful purpose
Which of the following would you rather be a part of?
  Getting a system in production
  Implementing a system so your practice would get the Meaningful Use incentives
  Using health IT to improve the health or your patients
Notes: Change starts with a deeply meaningful purpose
Which of the following would you rather be a part of?
  Getting a system in production,
  Implementing a system so your practice would get the Meaningful Use incentives, or
  Using health IT to improve the health or your patients?
My guess is the latter, because it is a purpose that is easy to engage with on a personal level. Improving human health is deeply meaningful work to many people.

## Slide 14: Key Concept 6:
Make and keep the gap between “as is” current reality and “to be” vision visible, and talk about it at every opportunity.
Making gaps visible maintains a “creative tension” as Peter Senge calls it, that motivates forward progress.
Notes: Make and keep the gap between “as is” and “to be” visible and talk about it at every opportunity. Making gaps visible maintains a “creative tension” as Peter Senge calls it, that motivates forward progress. In the Fifth Dimension Field Guide5, Senge likens holding this creative tension to holding a rubber band stretched between two hands, one representing the current reality and the other representing the envisioned state.
Reading from a passage from the Fifth Dimension Field Guide 5 by Peter Senge:
“People often have great difficulty talking about their visions, even when the visions are clear. Why? Because we are acutely aware of the gaps between our vision and reality. ‘I would like to start my own company,’ but ‘I don’t have the capital.’ Or, ‘I would like to pursue the profession that I really love,’ but ‘I’ve got to make a living.’ These gaps can make a vision seem unrealistic or fanciful. They can discourage us or make us feel hopeless. But the gap between vision and current reality is also a source of energy. If there was no gap, there would be no need for any action to move toward the vision. Indeed, the gap is the source of creative energy. We call this gap creative tension.
“Imagine a rubber band, stretched between your vision and current reality. When stretched, the rubber band creates tension, representing the tension between vision and current reality. What does tension seek? Resolution or release. There are only two possible ways for the tension to resolve itself: pull reality toward the vision or pull the vision toward reality. Which occurs will depend on whether we hold steady to the vision.” 5

## Slide 15: Key Concept 7:
Don’t pull.
If communications in your change efforts feel like a finger trap, i.e., you feel like you are selling the change, or you are pulling others along against their will, stop
people need to think through or reason through the reasons for and against change for themselves and come to an understanding of why change is needed
Notes: We all have a natural trouble detector. If communications in your change efforts feel like a finger trap, i.e., you feel like you are selling the change, or you are pulling others along against their will, stop. Peter Block, the author of Stewardship, Flawless Consulting,6 and The Answer to How is Yes,5 says it best as, “it is an assault to try and change someone’s mind”. Minds change through individual choice, not through coercion or force. This is probably the most fundamental of the key change concepts, but also, unfortunately, it may be the hardest to learn and practice.
A more tactical way to think about the “Don’t pull” concept is that people need to think through or reason through the reasons for and against change for themselves and come to an understanding of why change is needed. This is true for executives and for employees alike; it applies equally to anyone impacted by a change who is not directly involved in creating it. This should not be misconstrued as a statement that “everyone needs to agree with a change.” That may not be possible. It is a statement that everyone should have an opportunity to see the reasons for and against and the opportunity to think through them. A good question to ask people having difficulty with a change is, “given this situation, what would you do?”

## Slide 16: Thought Exercise
Think back to a time in your career when you woke up in the morning excited about coming to work.
List three things about your situation that made your job so engaging.
Notes: This is a small thought exercise to get you thinking about some of the Key Concepts so far. After these instructions, pause the slides and do the exercise. This should take you five minutes or so. First, think back to a time in your career (school, work or volunteer service) when you woke up in the morning excited about coming to work. Think about your work situation at that time. List three things about your situation that made your job so engaging.
When you are done, restart the slides, and we’ll go over some common responses to this exercise.
Pause the slides now.

## Slide 17: Thought Exercise
Common responses include
  Your own project / feeling of ownership
  You were making the decisions, / feeling of being in control
  Autonomy
  Trust with co-workers
Notes: Common responses to the exercise include
  your own project / feeling of ownership,
  you were making the decisions, / feeling of being in control,
  autonomy, and
  trust with co-workers.
The bottom line is that many people enjoy having a project or responsibility, having the authority and resources needed to do the job, and making the decisions. The same is true for managers, they are people too, and naturally, they also think it’s exciting to make all decisions. Sometimes, they don’t realize what they take away from employees when they do.

## Slide 18: Key Concept 8: The Engagement Gap4
Steering Committee
CEO
Team of the
“Best & the Brightest”
CEO
}
give everyone the benefit of the thought process, and the opportunity to influence
Notes: The engagement gap is a key component in change management. Dick and Emily Axelrod present this well.4 When initiating a change, many organizations select a team of “the best and the brightest” to go off and work on the needed change.
To expedite the project, the team reports to a steering committee for the change project, and the steering committee reports to a main executive. The idea is that these employees represent all employees. There is usually some requirement for communication back to and for soliciting input from their “home department”. Time and time again however, this process breaks down. The team stays engaged, and has the benefit of owning the project; they have an in-depth understanding of the constraints, etc. because they have spent many hours personally thinking and talking through all of the decisions.
The rest of the organization, however, has not had these experiences, has not thought through all of the issues, and has not become engaged. Often, the same phenomena happens with the steering committee or organizational leadership. When the results and recommendations are presented, the rest of the employees respond with shock and resistance, and organizational leadership often says “this is not what we wanted”.
Employees don’t trust what they haven’t thought through and leadership feels out of the loop. The Axelrods, in their book, Terms of Engagement call this an engagement gap. The only way to fix it is to give everyone the benefit of the thought process, and the opportunity to influence.

## Slide 19: Key Concept 9: Transparency
“…tell the truth, the whole truth and nothing but the truth…”
people often fail to trust what they do not see or know. People may not agree with a change, but they can understand it when provided all of the information. For example, why is the change needed, what the alternatives are, and why the proposed or decided alternative is the best
Notes: Change management is certainly not a court of law, the phrase, “…tell the truth, the whole truth and nothing but the truth…” used in the United States court system, illustrates a key change concept, transparency. Simply put, people often fail to trust what they do not see or know. People may not agree with a change, but they can understand it when provided all of the information. For example, why is the change needed, what the alternatives are, and why the proposed or decided alternative is the best.

## Slide 20: Pulling it all together
Change happens best when individuals have
  Deeply meaningful purpose
  Sincere invitation to influence
  Acknowledgement of opportunities for personal control or choice
  Transparency
  Shared understanding
Change is impacted by:
  Individuals and organizations
  Culture and trust
  How a change project is structured and managed
Notes: Pulling the Key Change concepts together, change happens best when individuals have:
  deeply meaningful purpose
  the opportunity to influence or otherwise exercise personal control or choice,
  transparency, and
  understanding.
Change is primarily impacted by:
  the individuals and organizations,
  culture and trust, and
  how the change project is structured.
If any of these things are out of kilter, it can undermine a change effort. If all of these are in place, a change effort has a good chance to succeed. Next, we will go over some planning tools and facilitation tools to help practitioners operationalize these principles.

## Slide 21: Applying All of This
Facilitation Plans and Tools
Notes: In Unit 7 of this Component, the student is
  provided strategies, tools, and aids for planning and conducting a decision-making meeting,
  presented examples of agenda and tables for conducting a walk through of a process, and
  provided tools for documenting decisions made and actions identified in a decision-making meeting.
In this lecture additional strategies, tools, and aids for facilitating the change process and implementation of the streamlined process redesign are provided. We also review and provide additional perspectives for meeting facilitation.

## Slide 22: Facilitation “F” Plan
A facilitation plan is an outline for how a meeting or an entire change effort will be run. A facilitation plan includes:
  Description of who is included.
  Description of how included individuals will be selected or invited.
  Schedule or agenda.
  Outline of what methods or tools will be used
  Description of how the rest of the organization will be kept up-to-date
  Description of how leadership will be kept in the loop
A facilitation plan should be made available to the entire organization to maintain transparency.
Notes: The facilitation plan may be created by the analyst or by an implementation or project manager.
This F plan is the first gesture of transparency and the start of building trust.
It outlines what will happen and how it will be managed; it is the social contract between the change leader and the people in an organization. The transparency displayed with the F plan is the change leader’s first opportunity for input and feedback. As we go forward, we will discuss facilitation as Big F, and use little “f” to demonstrate the differences of scope, intent and effort.

## Slide 23: Facilitation Plan Scenario
A mid-size internal medicine practice has decided to select, purchase and implement an EMR. They have hired you as a consultant for Process Analysis and Redesign. Your agreement with the practice is that you will provide instruction, training and oversight for members of their staff as they analyze their processes, redesign their processes around an EMR, and define the functionality that they need in an EMR.
You have already had an initial meeting with practice leadership and have had a tour and met the 75 person staff. At your next meeting, you will present the facilitation plan and get the analysis and redesign started.
Over the next several slides, we will look at “Big F” facilitation plan for the entire effort, and a “little f” agenda for the initial meeting.
Notes: Often, as in this scenario, the Process Analysis and Redesign Specialist guides the practice staff as they do the analysis and redesign, rather than doing it themselves. This scenario assumes this approach.
A mid-size internal medicine practice has decided to select, purchase and implement an EMR. They have hired you as a consultant for Process Analysis and Redesign. Your agreement with the practice is that you will provide instruction, training and oversight for members of their staff as they analyze their processes, redesign their processes around an EMR, and define the functionality that they need in an EMR.
You have already had an initial meeting with practice leadership and have had a tour and met the 75 person staff. At your next meeting, you will present the facilitation plan and get the analysis and redesign started.
Over the next several slides, we will look at “Big F” facilitation plan for the entire effort, and a “little f” agenda for the initial meeting.

## Slide 24: Big F
Group 1 work week:
Process inventory
Group 1 work week:
Process Analysis
Group 1 work week:
Process Redesign
Group 1 work week:
Finalize
Group 2: Weekly
Walkthroughs 1 hour
Leadership
briefing / debriefing
1 hour
Week 1
Week 2
Week 3
Week 4
Group one is the team that will be doing the work.
Group two is the rest of the organization.
Group one will spend a significant portion of their time analyzing and redesigning the practice processes, usually 50% to full time. Group two, the rest of the organization, must be kept up to date and “engaged” in the effort
Notes: The “Big F” is the plan for the entire effort. The way that I show a “Big F” is graphically and on one page; similar to the diagram above. The “Big F” communicates an overall timeline and work plan and importantly, is best when in communication with the rest of the organization, i.e., staff and providers not directly involved in the effort, as well as leadership.
The purpose is to 1) get input on the overall plan and 2) make sure that the plan is communicated to everyone so they will know what to expect. Here, we have assumed that the work needed by the practice can be accomplished in four weeks. The time for different practices will vary.
With 75 staff and additional providers and leadership, it will usually not be possible for everyone to be heavily involved in the effort. Here, we apply a “two-group” plan similar to those described by the Axelrods. Group one is the team that will be doing the work. Group two is the rest of the organization. Group one will spend a significant portion of their time analyzing and redesigning the practice processes, usually 50% to full time. Group two, the rest of the organization, must be kept up to date and “engaged” in the effort. In other words, group two needs to be efficiently walked through the planned process and the results as they are ready as well as the thought processes that produced them.
Importantly, You and leadership will need to communicate how group one was chosen. Some do this by invitation, e.g., an email to everyone describing the commitment and what is needed and inviting interested folks to step forward (if too many, sometimes, the number that can be spared to the effort will be randomly chosen). Others choose a “team” of the latter (remember the engagement gap). This depends on leadership, on the amount of effort that can be afforded, talent available, and provider and staff interests. Usually group one includes a representative from each of the major roles, or at least someone familiar with them.
The most important thing about the “Big F” is that it sets expectations for regular communication so that as the team goes through the thought process, the rest of the organization, and leadership goes through the process too. For a small 10-person practice, an elaborate plan like this is not necessary, the key criterion is that everyone is informed and has the opportunity to influence the project.

## Slide 25: Little f for Process Inventory
This occurs early in the process
Need
  To facilitate the team in creating a list of all of the major processes
Logistics
  Usually this is an initial meeting followed by someone creating the list or spreadsheet,
    Followed by group review and revision
Product
  Process inventory that can be provided at Walkthrough 1
Expect some revisions based on the broader review
Notes: The Little f (facilitation), for Process Inventory, occurs early in the process. It is needed to facilitate the team in creating a list of all of the major processes. It is usually used in an initial meeting followed by someone creating the list or spreadsheet, followed by group review and revision. The product of the Little f facilitation is a process inventory that can be provided at Walkthrough 1. Expect some revisions based on the broader review.

## Slide 26: Little f Week 1 Agenda
Introduction to overall project
  How the team was selected
  What their charge is
  The Big F plan
  Timeline and scope
Context diagram overview
Group context diagram creation
Think-pair-share
Sorting & grouping
Assignment of processes inventory work
Assignment for preparing for/conducting walkthrough
Notes: Recall the importance of a detailed agenda for meeting facilitation as presented in Unit 7.
Similarly, the Little f Week 1 Agenda should include:
  An Introduction to overall project
  How the team was selected
  What their charge is
  The Big F plan, and
  Timeline and scope.
This agenda should also include:
  Context diagram overview / review, and
  A Group context diagram creation.
It may be helpful to include exercises where the group will think-pair-share, perform sorting and grouping of recommended changes and make assignments of processes inventory work and assignments for preparing for and conducting walkthroughs.

## Slide 27: Little f for Process Analysis
Discussion:
  Process Inventory Results
Training:
  Flowcharts
Training:
  Analysis
  Spotting opportunities for improvement
Group exercise with 1 process
Independent work time
  With assigned processes
Paired feedback
Present each process and group discussion
Assignment
  Processes for analysis; preparing for/conducting walkthrough
Notes: Like week 1, training needs to occur, but this time, it is training about how to do a process diagram and analysis. Also there is group work on an example process and opportunities for discussion and feedback. It is anticipated that clinic staff will go off on their own and complete the analysis for discussion at the next meeting.

## Slide 28: Little f Redesign
Training:
  Common EHR functionality
  Matching analysis results to EHR functionality
Group exercise with one process
Independent work time with assigned processes
Paired feedback
Present each process and group discussion
Assignment
  Processes for redesign
  Preparing for/conducting walkthrough
Notes: Like weeks 1 and 2, training needs to occur, but this time, it is training on common EHR functionality, and on how to match functionality to clinic needs and analysis results. Also similar to weeks 1 and 2, there is group work on an example process and opportunities for discussion and feedback. It is anticipated that clinic staff will go off on their own and complete the redesign for discussion at the next meeting.

## Slide 29: Little f post-Week 1 Walkthrough
Introduction to overall project
  How the team was selected
  What their charge is
  The Big F plan
  Timeline and scope
Context diagram exercise
  Create one as a group
  Pin-the-tail on the donkey
Process Inventory
  What did we miss
Notes: The Walkthrough is a meeting with the broader organization, i.e., staff who are not on the team to keep them up to date about the project’s progress and current thinking. It is also an opportunity to keep all staff engaged and to get feedback on the plan. Thus, all participants should be encouraged to talk as much as the project team! For example, instead of presenting the context diagram, cut the shapes up and get the group to put it together (pin-the-tail-on the donkey), or have them take five minutes and individually draw one, then “shout out” components. For process inventory, pass out the list, have people look at it for five minutes and identify things missed. There should be a walkthrough every time the team finishes a major project.

## Slide 30: Little f Leadership Briefing / Debriefing
Brief review of progress
Presentation of challenges
Review and “what did we miss” exercises
Engaging questions:
  Any surprises based on what’s presented
  Get help strategizing about challenges
  Leadership should have input into prioritizing processes for analysis and redesign
Notes: Don’t forget about Leadership – they need to be engaged as well.
For a Leadership Agenda try:
Brief review of progress
Presentation of challenges
Review & “what did we miss” exercises
Engaging questions:
  Any surprises based on what’s presented?
  Get help strategizing about challenges
  Leadership should have input into prioritizing processes for analysis and redesign
During the project you should keep a list of things that leadership should decide or have input into, e.g., “do we want an EHR that also has Patient Management System (PMS) functionality, or should we stay on same PMS and build an interface?” It is the team’s responsibility to make advantages and disadvantages of such decisions clear.

## Slide 31: Summary
The method and plan don’t matter as much as adhering to principles of Change Management
The example method here Big F/little f and the two group process is only one example
Notes: In summary, the method and plan don’t matter as much as adhering to principles of change management.
The example method used in this unit was the Big F/little f. The two group process is only one example.

## Slide 32: Topics – Unit 10.10
Common process changes
Implementation plan components
Communication for implementation
Common implementation problems
Evaluating the new process
Notes: The topics covered in Unit 10 include common process changes, implementation plan components, communication for implementation, common implementation problems, and evaluating the new process.

## Slide 33: Common Process Changes
From manual to electronic prescribing
From receptionist to web-based appointment scheduling
From manual to automated appointment reminder calls
From manual tracking of test results to automated result tracking
From paper to electronic patient charts
From paper to electronic test ordering
Notes: To ground ourselves in concrete ideas of what to expect in process change implementation and in this unit, we’ll start with examples of common process changes. Some examples are:
  From manual to electronic prescribing
  From receptionist to web-based appointment scheduling
  From manual to automated appointment reminder calls
  From manual tracking of test results to automated result tracking
  From paper to electronic patient charts
  From paper to electronic test ordering.
While each of these is just a sentence, changes must be considered and thought through from many perspectives and eventualities. This thinking occurs in the analysis and re-design phase. The implementation planning is a group/ team activity. Communication of the implementation plan and execution resulting in new improved process will involve many people.

## Slide 34: Implementation Plan
The implementation plan serves as a map for everyone involved in changing a process. It covers what steps everyone will need to take, what to expect and what to do when things don’t go as planned.
©iStockphoto.com/nahm0001
Notes: The implementation plan documents the who, what, where, when, how, and why of the process change. It serves as a map that helps the clinic staff, leadership, and analyst get from the old process to the new one.

## Slide 35: Implementation Plan Components
Reason for the change
Summary of what will be different
Sequence of implementation tasks
An implementation schedule for the entire implementation phase
  Responsible parties
  Each implementation task
Statement of how the process will be managed
Contact information for who to call when problems arise
Description of how the process change will be evaluated
Notes: An implementation plan contains the following components:
  Reason for the change.
  Summary of what will be different with reference to the “as is” and “to be” documentation, where it is located in the documents or in an appendix. Where the process change is significant, this may include step by step instructions for new workflows.
  Sequence of implementation tasks to be accomplished. These can include walkthroughs, training, production and distribution of job aids, software changes or “go-live” of new systems.
  Responsible parties for each implementation task.
  An implementation schedule for the entire implementation phase, and statement of how the process will be managed.
  Contact information for who to call when problems arise and
  Description of how the process change will be evaluated (an evaluation plan).
An implementation plan does not need to be a long document. Its purpose is to document what will happen, how and when it will happen in a way such that if the implementation plan is followed, the new process will become a reality. The length and detail level should be comparable to the size of the change and number of people impacted. An example implementation plan that shows these components is included in your course materials, and will be reviewed on the next few slides. But first, we will do an exercise.

## Slide 36: Exercise
A practice of 50 staff and providers is implementing an automated appointment reminder system.
Review the implementation plan components on the previous slide.
Take 10-15 minutes and on one page of paper, jot down your ideas for each section.
Notes: You already know enough to draft an implementation plan for an appointment reminder system. After these instructions, pause the slides and do the exercise.
A practice of 50 staff and providers is implementing an automated appointment reminder system. Review the implementation plan components on the previous slide. You may want to go back and print out the slide. Take 10-15 minutes and on one page of paper, jot down your ideas for each section. Restart the slides when you are done. Pause the slides now.

## Slide 37: Example Implementation Plan
Reason for the change
In efforts to decrease our “no show” rate, Big City Medical Practice is implementing automated appointment reminder calls. Due to lack of staff, our practice has not commonly made appointment reminder calls. With our new system, we are able to do this.
Notes: An example “Reason for the Change” statement for an implementation plan for automated appointment reminders might be:
“In efforts to decrease our ‘no show’ rate, Big City Medical Practice is implementing automated appointment reminder calls. Due to a lack of staff, our practice has not commonly made appointment reminder calls. With our new system, we are now able to do this.”

## Slide 38: Example Implementation Plan (cont)
What will be different?
Our patients are not used to receiving reminder calls. Starting in two weeks (Friday October 29, 2011) each patient that schedules an appointment will receive notice that they will receive a reminder call. This notice will be generated automatically for appointments scheduled on line. For appointments made over the phone or in person, front desk staff scheduling the patient will inform them. Patients with appointments that were scheduled prior to Monday October 30, 2017 will not receive reminder calls.
We are informing everyone in the practice with patient contact of this new practice in case patients have questions or comments about their reminder call. For more information, process diagrams and documentation describing details of this change are available in the break room.
Other than notifying patients of this change and being alert for patient questions or comments, there are no significant changes to anyone’s workflow.
Notes: An example of a statement for what will be different is:
What will be different?
“Our patients are not used to receiving reminder calls. Starting in two weeks (Friday October 29, 2011) each patient that schedules an appointment will receive notice that they will receive a reminder call. This notice will be generated automatically for appointments scheduled on line. For appointments made over the phone or in person, front desk staff scheduling the patient will inform them. Patients with appointments that were scheduled prior to Monday October 30, 2011 will not receive reminder calls.
“We are informing everyone in the practice with patient contact of this new practice in case patients have questions or comments about their reminder call. For more information, process diagrams and documentation describing details of this change are available in the break room.
Other than notifying patients of this change and being alert for patient questions or comments, there are no significant changes to anyone’s workflow.”

## Slide 39: Example Implementation Plan (cont)
Time Schedule of Events & Responsibilities
Mon, Oct 4 Final system test (A. Smith)
Tues, Oct 5-15 (Fri.) Address issues from testing / retest (Vendor)
Mon, Oct 18 Live installation (Vendor)
Wed, Oct 20 Data migration and migration test (A. Smith)
Thurs, Oct 21-25 (Mon.) Contingency time (C. Doe)
Mon, Oct 25 Talking points ready for registration Review (C. Doe)
  Fri, Oct 29 Go live for on-line and in-person notices (Registration)
Notes: An example time schedule and responsibilities for implementation of an automated appointment system is shown here.

## Slide 40: Example Implementation Plan (cont)
Implementation management
The implementation will be managed by C. Doe from our local Regional Extension center with support from Amy Smith, our local IT technical support person. Changes to the schedule above will be posted in the break room.
Notes: An example of the management statement includes who will actually be responsible for the implementation management.
For instance, “The implementation will be managed by C. Doe from our local Regional Extension center with support from Amy Smith, our local IT technical support person. Changes to the schedule above will be posted in the break room.”

## Slide 41: Example Implementation Plan (cont)
When problems arise
For any unexpected problems and if you notice or patients mention unusual system behavior, please contact Amy Smith at (555) 555-5555 or C. Doe at (777) 777-7777. If problems occur after hours, report through the after hours number at (888) 888-8888.
Notes: An example of the “what to do when problems arise” section for implementation of an automated appointment reminder system, might include wording such as the following: “For any unexpected problems and if you notice or patients mention unusual system behavior, please contact Amy Smith at (555) 555-5555; or C. Doe at (777) 777-7777. If problems occur after hours, report through the after hours number at (888) 888-8888.”

## Slide 42: Example Implementation Plan (cont)
Evaluation
This process change will be evaluated by the decrease in no show visits and by addition of a question to the December Patient satisfaction survey.
Notes: An example of the evaluation description for implementation of an automated appointment reminder system might include, “This process change will be evaluated by the decrease in no show visits and by addition of a question to the December patient satisfaction survey.”

## Slide 43: Communication of an Implementation Plan
“Tell me and I’ll forget;
show me and I may remember;
involve me and I’ll understand.”
– Chinese Proverb
keep everyone involved throughout the process
Notes: At the point in a process redesign when an analyst is crafting an implementation plan, hopefully the impacted people will already know about the change or have otherwise been involved in creating the change in some way. In this case, the communication about the implementation will be easy and expected by all. If not, expect objections either to the plan or the new process, or both. In this event, the communication and implementation will take longer, and may result in changes to the process or plan. The way to prevent such a situation is to, at a minimum, keep everyone involved throughout the process. Remember our old adage from unit 9:
“Tell me and I’ll forget;
show me and I may remember;
involve me and I’ll understand.”

## Slide 44: What People Need to Know
What is happening
Why is the change taking place
How they will be affected
  Address each task or activity that will be added, changed or will go away
How the change will impact workflow or responsibilities
How will the change take place
What if anything different will the patients see
Notes: When communicating an implementation plan, it is important to keep in mind what things people need to know.
As in the automated appointment reminder system implementation plan example, when the change is minor, the plan itself can be short and can double as a notice, i.e., communication. The main goal is to give people information about:
  What is happening.
  Why is the change taking place. (Examples of this might include to enable patient self-management or control, to increase safety, quality or efficiency of care, for sustainability of the practice, or to achieve meaningful use.)
  How they will be affected. (This is often best accomplished by addressing each task or activity that will be added, changed or go away.)
  How the change will impact their job workflow or responsibilities.
  How will the change take place.
  What if anything different will the patient see.
  Communication can occur via email, posted notices, or staff meetings. In person communication provides opportunity for attendees to ask questions and for the presenter to get feedback that might increase the success of the project.

## Slide 45: Job Aids
Talking points
Check lists
Written procedures
Or cheat sheets
©iStockphoto.com/nahm0001
Notes: When process changes necessitate new steps or tasks, job aids may be helpful. For example, in the automated appointment reminder system implementation, the front desk receptionist needed to notify people scheduling appointments that they would be receiving a reminder call. A job aid with talking points (answers to common questions the receptionist might be asked) was provided as a job aid. Job aids might include: Talking points, check lists, written procedures, or cheat sheets (memory aids to rescue people when they forget what to do, or descriptions of new system features for common tasks).
The type and extent of the job aid depend on how extensive the change is. The creation and training on job aids should be included in the implementation plan.

## Slide 46: Training
Process changes require new skills
People will be required to use new tools
  Instrumentation
  New forms
  New software
When it is necessary for people to execute process steps the same way
Notes: When process changes require new skills like using new software, a different way of doing something like completing a lab sample requisition form on the computer versus a paper one, training should occur. Training should also occur when multiple ways of doing something are possible but the job requires that everyone does it the same way. The formality of the training depends on the extensiveness of the change and the number of people that need to be trained and can include class room style training, one-on-one training, or web-based modules for software training.
Time for development or procurement of training should be included in the implementation plan, as should time for the training to occur.

## Slide 47: Be Present
Implementation support personnel should be on site or readily available to coach staff through problems that arise, to troubleshoot, and to facilitate decision making about interim work-arounds and activation of contingency plans in the face of serious problems.
©iStockphoto.com/nahm0001
Notes: An implementation plan does not stand alone. After all of the planning and communication have occurred, it is time for execution, i.e., to execute the plan and to make the new process a reality. Most importantly, unexpected things will occur in even the best planned and managed implementations. Importantly, the person in charge of the implementation needs to be present, visible and available the first few days of a new process to help resolve any problems that occur.

## Slide 48: Process Implementation Problems
Planning
Communication
Process itself
Software
©iStockphoto.com/nahm0001
While we go to great effort to plan and prepare so that problems will be small and infrequent, problems will occur with every implementation. Problems occur in planning, communication, the design of a new process, i.e., things were left out or not accounted for, or problems in the software itself. The important thing is not that problems occur, but that 1) everything reasonable was done to plan and prepare to prevent problems, and 2) that problems are addressed swiftly.
Notes: It is never fun when problems do occur. While we go to great effort to plan and prepare so that problems will be small and infrequent, problems will occur with every implementation. Problems occur in planning, communication, the design of a new process, i.e., things were left out or not accounted for, or problems in the software itself. The important thing is not that problems occur, but that 1) everything reasonable was done to plan and prepare to prevent problems, and 2) that problems are addressed swiftly.

## Slide 49: Exercise
Take five minutes and review the example implementation plan for the automated appointment reminder system
List two possible problems that could occur in each of:
  planning
  communication
  the process, or
  in the software
Notes: Take five minutes and review the example implementation plan for the automated appointment reminder system.
List two possible problems that could occur in each of the following areas:
  planning
  communication
  the process, or
  In the software
We will review some common causes of problems on the next slide. Pause the slides now. When you have finished restart the slides.

## Slide 50: Review of Exercise
Planning
  Failure to account for other activities
  Forgot to include migration of legacy data to new system
Communication
  Lack of communication to practice leadership
  Lack of communication with people involved in the plan
Process itself
  Failure to account for likely exceptions
Software
  Lack of testing
  Found problems in testing and changes can’t be made quickly enough
Notes: Examples of possible problems include:
Planning
  Timeline didn’t account for other activities such as vacations of key people, or activities were planned for during the work day that would have been better done during off hours
  Forgot to include migration of legacy data to new system
Communication
  Lack of communication to practice leadership
  Lack of communication ahead of time with people involved in the plan
Process itself
  Didn’t take into account likely exceptions such as what about people who made appointments before the change
  What happens if the system gets a voicemail
  How does the system know it’s the person
  Forgetting to have a process for turning reminders off when appointments are moved
Software
  Lack of testing
  Found problems in testing and changes can’t be made quickly enough
You may have noted other problems that are equally as valid!

## Slide 51: Evaluation
Patient wait times
  e.g., From registration to seeing a provider
Total visit time
Percentage of same day appointment accommodations
Increased clinic capacity
  Higher number of encounters per day per provider
Patient satisfaction measures
Provider/staff time spent retrieving information
Provider/staff time spent documenting
Provider/staff satisfaction
Percentage of first-time-file claims returned
Notes: We mentioned evaluation as an implementation plan component. Process changes should be evaluated in some way to make sure that they had the intended impact. The evaluation should be a measure of achievement of the “reason for change.” In the simple example of implementation of an automatic appointment reminders system, the reason for the system and process change was a higher than desirable “no show” rate. The metric for evaluating the change was “decrease in the ‘no show’ rate”. Because the new process impacted patients, a question about the reminder calls was added to the next cycle of the patient satisfaction survey. Some examples of things that can be measured to evaluate a process change include:
  Patient wait times, e.g., from registration to seeing a provider,
  Total visit time,
  Percentage of same day appointment accommodations,
  Increased clinic capacity (higher number of encounters per day per provider),
  Patient satisfaction measures,
  Provider/staff time spent retrieving information,
  Provider/staff time spent documenting,
  Provider/staff satisfaction, and
  Percentage of first-time-file claims returned.
The value gained from the evaluation must be weighed against the effort required to collect the data for the evaluation. Vendors should be questioned about data available for evaluation of planned process changes.

## Slide 52: References
1. Janssen, Claes F., available from http://www.claesjanssen.com/four-rooms/about-the-four-rooms-of-change/index.shtml
2. Gall, John, MD, Systematics. New York, New York: Quadrangle; 1977.
3. Senge, Peter M., Kleiner, Art, Roberts, Charlotte, Ross, Richard, B. Rick, Smith, Bryan J.. The Fifth Discipline Fieldbook: Strategies and Tools for Building a Learning Organization. New York, New York: Doubleday, 2000.
4. Axelrod, Richard H., Terms of Engagement: Changing the Way We Change Organizations. San Francisco, California: Berrett-Koehler Publishers: 2002.
5. Peter Block, The Answer to How is Yes: Acting on What Matters. San Francisco, California: Ingram Pub Services; 2003.
6. Block, Peter, Nowlan, Janis, Flawless Consulting: A Guide to Getting Your Expertise Used. 2nd ed. New York, New York: Jossey-Bass/Pfeiffer; 1999.
7. Koestenbaum, Peter, Leadership: The Inner Side of Greatness. San Francisco, California: Jossey-Bass, Inc., 1991.
8. Senge, Peter, Kleiner, Art, Roberts, Charlotte, Roth, George, Ross, Rick, Smith, Bryan, The Dance of Change. New York, New York: Doubleday; 1999.
Notes: These references were used in this unit.